## Hoja1
DMAIC Phase | Epic | User Story | Priority (High/Med/Low) | Status (To Do/In Progress/Done) | Notes
Define | Problem Identification | As a project team, we need to define key production inefficiencies using data. | High | Done | Based on Excel analysis
Measure | Data Collection | As a project team, we need to track production and downtime to identify major bottlenecks. | High | Done | Used daily/hourly data
Analyze | Root Cause Analysis | As a team, we need to determine the top reasons for downtime using Pareto analysis. | High | Done | Identified top 3 downtime causes
Analyze | Process Flow Mapping | As a process engineer, I want to visualize the production flow to detect inefficiencies. | High | Done | Created process diagram
Improve | Workforce Efficiency | As a manager, I want to restructure rest breaks to reduce downtime. | High | In Progress
Improve | Equipment Reliability | As an operator, I want a preventive maintenance schedule to minimize failures. | High | To Do
Improve | Process Optimization | As a production planner, I want to reduce changeover times between batches. | Medium | To Do
Improve | Standardized Workflows | As a supervisor, I want clear procedures to ensure consistency. | Medium | To Do
Control | KPI Tracking | As a project lead, I want to track KPIs to measure the impact of improvements. | High | In Progress
Control | Documentation & Training | As a quality manager, I want training materials to ensure long-term adherence to improvements. | Medium | To Do